## Sheet1
Discord Bot Timeline - Gantt Chart | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Evaluate Requirements
Determine what moderators need | bar: Week 1
Understand the basics of the Discord API | bar: Week 2
Design
Rough outline of desired functionality | bar: Week 2
Research and Develop
Create a bot account | bar: Week 3
Create basic testing server structure | bar: Week 3
Programming | bar: Week 3 to Week 10
Deployment testing | bar: Week 7 to Week 11
Deliverables
Topic proposal | bar: Week 1
SPMP | bar: Week 4
Gantt chart | bar: Week 4
Design review meetings | bar: Week 4 to Week 5
Tool selection review meeting | bar: Week 4 to Week 5
Milestone review | bar: Week 6
System test plan | bar: Week 7 to Week 11
Final project presentation | bar: Week 12
Testing
Integration testing | bar: Week 8 to Week 11
Full Public Releasse
Complete documentation | bar: Week 10 to Week 11
Complete command guide | bar: Week 10 to Week 11
Open GitHub repository | bar: Week 12