## Sheet1
Commander: Discord Bot
Milestone Review
Milestones Set in SPMP | Expected Date of Completion | Actual Date of Completion | Reason (if not achieved by expected data)
Code / Research
Determine what moderators need | Week 1 | Week 1
Understand the basics of the Discord API | Week 2 | Week 2
Rough outline of desired functionality | Week 2 | Week 2
Create a bot account | Week 3 | Week 3
Create basic testing server structure | Week 3 | Week 3
Programming | Week 10 | Week 11-12 | Adding polish and extra functionality to the bot in my free time.
Deployment testing | Week 11 | Week 11-12 | Deploying to live host ASAP with hosting already secured. Not too many difficulties are anticipated due to my group project experience of hosting our website.
Integration testing | Week 11 | Week 11
Documentation
Topic proposal | Week 1 | Week 1
SPMP | Week 4 | Week 4
Gantt chart | Week 4 | Week 4
Design review meeting | Week 5 | Week 5
Tool selection review | Week 5 | Week 8 | Tool selection changed from using a Python library to a JavaScript library plus the usage of TypeScript.
Milestone review | Week 6 | Week 11 (current week) | Did not understand at first what the goals of the milestone review were. It was necessary for me to complete this near the end of the project.
System test plan | Week 11 | Week 11 (current week)
Final project presentation | Week 12 | Week 12 | Upcoming
Make GitHub respository public | Week 12 | Week 12 | Upcoming
Complete command guide | Week 11 | Week 11-12 | Programming not yet finalized. But, full documentation already exists for all current commands, and documentation for all future commands will be provided.
Christian Sauls | 2020-04-30 |  | Software Engineering - COSC 412-101